## Tasks
Task_Name | Description | Start_Date | End_Date | Duration_Days | Assignee | Email | Priority | Status | Labels | Dependencies
KOM - Zenzic and MSP | KOM - Zenzic and MSP | 2025-05-01 | 2025-05-01 | 30 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.1
Software Tools Selection and basic testing | Software Tools Selection and basic testing | 2025-05-01 | 2025-06-01 | 60 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | NA
Hardware Tools Selection and basic testing | Hardware Tools Selection and basic testing | 2025-06-01 | 2025-07-01 | 60 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | NA
Meeting AI advisors on project setup | Meeting AI advisors on project setup | 2025-06-01 | 2025-07-01 | 60 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.1
Route 10 Deliveres | Route 10 Deliveres | 2025-04-01 | 2025-04-01 | 390
Proof of concept algorithm and visual output for indicative large-scale automated assessment (eg regional). | Proof of concept algorithm and visual output for indicative large-scale automated assessment (eg regional). | 2025-06-01 | 2025-06-01 | 30 | Collaborators - Route 10 | collaborators@route10.com |  |  |  | 1.1
Proof of concept algorithm with manual assistance and numerical/agentic output for indicative small-scale automated assessment (eg local) | Proof of concept algorithm with manual assistance and numerical/agentic output for indicative small-scale automated assessment (eg local) | 2025-06-01 | 2025-06-01 | 30 | Collaborators - Route 10 | collaborators@route10.com |  |  |  | 2.1
Report Including - Background Metholodogy and Conlcusions | Report Including - Background Metholodogy and Conlcusions | 2025-07-01 | 2025-08-01 | 60 | Collaborators - Route 10 | collaborators@route10.com |  |  |  | 2.1
Provide code and documentations to Atera A. | Provide code and documentations to Atera A. | 2025-07-01 | 2025-08-01 | 60 | Collaborators - Route 10 | collaborators@route10.com |  |  |  | 2.2, 2.3
Front End Application | Front End Application | 2025-04-01 | 2025-04-01 | 390
Exploratory Data Analysis | Exploratory Data Analysis | 2025-08-01 | 2025-10-01 | 90 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.2
Develop visualisation and users intefaces | Develop visualisation and users intefaces | 2025-08-01 | 2025-10-01 | 90 | Application Developer | app.developer@ateraanalytics.com |  |  |  | 1.2, 3.1
Rendering of POC Visualisations at interface | Rendering of POC Visualisations at interface | 2025-09-01 | 2025-10-01 | 60 | Application Developer | app.developer@ateraanalytics.com |  |  |  | 3.2
Visualisation of Route 10 Report | Visualisation of Route 10 Report | 2025-09-01 | 2025-10-01 | 60 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 2.1,2.2,2.3
Project Management and Setup | Project Management and Setup | 2025-04-01 | 2025-04-01 | 390
Scope and Goal Setting | Scope and Goal Setting | 2025-05-01 | 2026-02-01 | 120 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.1
Quarterly Objectives Review & Planning | Quarterly Objectives Review & Planning | 2025-05-01 | 2026-02-01 | 120 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.1
Session with advisors & stakeholders | Session with advisors & stakeholders | 2025-06-01 | 2026-03-01 | 120 | Whole Team | team@ateraanalytics.com |  |  |  | 1.4
Web Tools Setup & Integration Environment | Web Tools Setup & Integration Environment | 2025-06-01 | 2026-01-01 | 240 | Lead & Application Developer | lead.appdev@ateraanalytics.com |  |  |  | 1.2
Training & Technical Events | Training & Technical Events | 2025-05-01 | 2026-02-01 | 150 | Whole Team | team@ateraanalytics.com |  |  |  | 4.1
QRM 1 with Monitoring Officer | QRM 1 with Monitoring Officer | 2025-08-01 | 2025-04-01 | 120 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.1
Hardware Setup | Hardware Setup | 2025-06-01 | 2026-01-01 | 150 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.3
Data Integration and Architecture | Data Integration and Architecture | 2025-04-01 | 2025-04-01 | 390
CAM Operations Data Enablement | CAM Operations Data Enablement | 2025-06-01 | 2026-01-01 | 150 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.2, 4.1
End to End Data Architecture Design | End to End Data Architecture Design | 2025-07-01 | 2026-01-01 | 120 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.2, 5.1
Validate EV CAM performance data | Validate EV CAM performance data | 2025-08-01 | 2025-12-01 | 90 | Contractor | contractor@ateraanalytics.com |  |  |  | 5.1
Digital Data Model Definition | Digital Data Model Definition | 2025-07-01 | 2026-01-01 | 120 | AI Specialist | ai.specialist@ateraanalytics.com |  |  |  | 5.2
Data Integration with External Sources | Data Integration with External Sources | 2025-09-01 | 2025-12-01 | 120 | Application and Data Dev | app.datadev@ateraanalytics.com |  |  |  | 1.2,5.2,5.4
AI Data Enrichment & Integration of Data Sets | AI Data Enrichment & Integration of Data Sets | 2025-10-01 | 2026-01-01 | 120 | Lead & Application Developer | lead.appdev@ateraanalytics.com |  |  |  | 5.2,5.5
Visualisation of Route Navigation Data | Visualisation of Route Navigation Data | 2025-10-01 | 2026-01-01 | 90 | AI Specialist | ai.specialist@ateraanalytics.com |  |  |  | 5.4,5.6
CAM Integration and Testing | CAM Integration and Testing | 2025-04-01 | 2025-04-01 | 390
Atera A. CAM Data API Connectivity | Atera A. CAM Data API Connectivity | 2025-08-01 | 2026-02-01 | 120 | PM/Lead | pm.lead@ateraanalytics.com |  |  |  | 1.2, 5.3
Design for CAM 5G Data Processing | Design for CAM 5G Data Processing | 2025-08-01 | 2025-10-01 | 90 | Lead & Application Developer | lead.appdev@ateraanalytics.com |  |  |  | 6.1
Prepare Data for AI Network Models | Prepare Data for AI Network Models | 2025-09-01 | 2025-11-01 | 90 | Lead & Application Developer | lead.appdev@ateraanalytics.com |  |  |  | 6.2
Design Machine Learning Path Planning | Design Machine Learning Path Planning | 2025-10-01 | 2026-01-01 | 120 | AI Specialist | ai.specialist@ateraanalytics.com |  |  |  | 5.6, 5.7
Train Models for Remote control Driving KPIs | Train Models for Remote control Driving KPIs | 2025-11-01 | 2026-02-01 | 120 | PM/Lead & AI Specialist | pm.aispecialist@ateraanalytics.com |  |  |  | 6.1,5.6
Validate AI Models | Validate AI Models | 2025-12-01 | 2026-03-01 | 120 | Lead & AI Specialist | lead.aispecialist@ateraanalytics.com |  |  |  | 6.4,6.5
NVidia Digital Twin module deployment | NVidia Digital Twin module deployment | 2026-01-01 | 2026-03-01 | 90 | Contractor | contractor@ateraanalytics.com |  |  |  | 1.2,1.3, 6.4
Automated Data acces via API | Automated Data acces via API | 2026-03-01 | 2026-03-01 | 30 | Application and Data Dev | app.datadev@ateraanalytics.com |  |  |  | 1.2,5.7,6.7
Final Delivery | Final Delivery | 2025-04-01 | 2025-04-01 | 390
Full implementation of platform | Full implementation of platform | 2026-03-01 | 2026-03-01 | 30 | Whole Team | team@ateraanalytics.com |  |  |  | 1,2,3,4,5,6
Project Reporting and Presentation | Project Reporting and Presentation | 2025-04-01 | 2025-04-01 | 30 | Whole Team | team@ateraanalytics.com |  |  |  | 7.1