## Sheet1
Task_Name | Description | Start_Date | End_Date | Duration_Days | Assignee | Priority | Status | Labels
Project Kickoff Meeting | Initial project meeting with all stakeholders to align on goals and timeline | 2025-01-15 | 2025-01-15 | 1 | Project Manager (pm@company.com) | High | To Do | planning,kickoff,meeting
Requirements Gathering | Collect and document all functional and non-functional requirements | 2025-01-16 | 2025-01-19 | 4 | Business Analyst (ba@company.com) | High | To Do | requirements,analysis,documentation
System Architecture Design | Design overall system architecture including tech stack decisions | 2025-01-20 | 2025-01-26 | 7 | John Smith (john.smith@company.com) | High | To Do | architecture,design,planning
Frontend Development | Develop user-facing components using React and TypeScript | 2025-01-27 | 2025-02-09 | 14 | jane.doe@company.com | High | To Do | frontend,react,development
Backend API Development | Create REST APIs for all business logic and data operations | 2025-01-27 | 2025-02-09 | 14 | mike.johnson@company.com | High | To Do | backend,api,development
Database Setup | Setup PostgreSQL database with initial schema and migrations | 2025-01-23 | 2025-01-25 | 3 | Sarah Lee (sarah.lee@company.com) | Medium | To Do | database,postgresql,setup
UI/UX Design | Create wireframes and high-fidelity mockups for all screens | 2025-01-22 | 2025-02-05 | 15 | alex.designer@company.com | Medium | To Do | design,ui,ux,mockups
Integration Testing | Test integration between frontend, backend, and database | 2025-02-10 | 2025-02-16 | 7 | QA Team (qa-team@company.com) | High | To Do | testing,integration,qa
Security Audit | Perform security review and penetration testing | 2025-02-17 | 2025-02-21 | 5 | Security Team (security@company.com) | High | To Do | security,audit,compliance
Deployment Setup | Configure CI/CD pipeline and production environment | 2025-02-20 | 2025-02-23 | 4 | DevOps Engineer (devops@company.com) | High | To Do | devops,deployment,cicd
User Documentation | Write comprehensive user guides and API documentation | 2025-02-15 | 2025-02-23 | 9 | tech.writer@company.com | Medium | To Do | documentation,training,users
Training Sessions | Conduct training sessions for end users and administrators | 2025-02-24 | 2025-02-28 | 5 | Training Coordinator (training@company.com) | Medium | To Do | training,education,users