## Tasks
Task ID | Task Name | Assignee | Email | Dependencies | Start Date | End Date
1.1 | KOM - Zenzic and MSP | PM/Lead | pm.lead@ateraanalytics.com | 1.1 | May | May
1.2 | Software Tools Selection and basic testing | PM/Lead | pm.lead@ateraanalytics.com | NA | May | Jun
1.3 | Hardware Tools Selection and basic testing | PM/Lead | pm.lead@ateraanalytics.com | NA | Jun | Jul
1.4 | Meeting AI advisors on project setup | PM/Lead | pm.lead@ateraanalytics.com | 1.1 | Jun | Jul
2 | Route 10 Deliveres |  |  |  | Apr | Apr
2.1 | Proof of concept algorithm and visual output for indicative large-scale automated assessment (eg regional). | Collaborators - Route 10 | collaborators@route10.com | 1.1 | Jun | Jun
2.2 | Proof of concept algorithm with manual assistance and numerical/agentic output for indicative small-scale automated assessment (eg local) | Collaborators - Route 10 | collaborators@route10.com | 2.1 | Jun | Jun
2.3 | Report Including - Background Metholodogy and Conlcusions | Collaborators - Route 10 | collaborators@route10.com | 2.1 | Jul | Aug
2.4 | Provide code and documentations to Atera A. | Collaborators - Route 10 | collaborators@route10.com | 2.2, 2.3 | Jul | Aug
3 | Front End Application |  |  |  | Apr | Apr
3.1 | Exploratory Data Analysis | PM/Lead | pm.lead@ateraanalytics.com | 1.2 | Aug | Oct
3.2 | Develop visualisation and users intefaces | Application Developer | app.developer@ateraanalytics.com | 1.2, 3.1 | Aug | Oct
3.3 | Rendering of POC Visualisations at interface | Application Developer | app.developer@ateraanalytics.com | 3.2 | Sep | Oct
3.4 | Visualisation of Route 10 Report | PM/Lead | pm.lead@ateraanalytics.com | 2.1,2.2,2.3 | Sep | Oct
4 | Project Management and Setup |  |  |  | Apr | Apr
4.1 | Scope and Goal Setting | PM/Lead | pm.lead@ateraanalytics.com | 1.1 | May | Feb
4.2 | Quarterly Objectives Review & Planning | PM/Lead | pm.lead@ateraanalytics.com | 1.1 | May | Feb
4.3 | Session with advisors & stakeholders | Whole Team | team@ateraanalytics.com | 1.4 | Jun | Mar
4.4 | Web Tools Setup & Integration Environment | Lead & Application Developer | lead.appdev@ateraanalytics.com | 1.2 | Jun | Jan
4.5 | Training & Technical Events | Whole Team | team@ateraanalytics.com | 4.1 | May | Feb
4.6 | QRM 1 with Monitoring Officer | PM/Lead | pm.lead@ateraanalytics.com | 1.1 | Aug | Apr
4.7 | Hardware Setup | PM/Lead | pm.lead@ateraanalytics.com | 1.3 | Jun | Jan
5 | Data Integration and Architecture |  |  |  | Apr | Apr
5.1 | CAM Operations Data Enablement | PM/Lead | pm.lead@ateraanalytics.com | 1.2, 4.1 | Jun | Jan
5.2 | End to End Data Architecture Design | PM/Lead | pm.lead@ateraanalytics.com | 1.2, 5.1 | Jul | Jan
5.3 | Validate EV CAM performance data | Contractor | contractor@ateraanalytics.com | 5.1 | Aug | Dec
5.4 | Digital Data Model Definition | AI Specialist | ai.specialist@ateraanalytics.com | 5.2 | Jul | Jan
5.5 | Data Integration with External Sources | Application and Data Dev | app.datadev@ateraanalytics.com | 1.2,5.2,5.4 | Sep | Dec
5.6 | AI Data Enrichment & Integration of Data Sets | Lead & Application Developer | lead.appdev@ateraanalytics.com | 5.2,5.5 | Oct | Jan
5.7 | Visualisation of Route Navigation Data | AI Specialist | ai.specialist@ateraanalytics.com | 5.4,5.6 | Oct | Jan
6 | CAM Integration and Testing |  |  |  | Apr | Apr
6.1 | Atera A. CAM Data API Connectivity | PM/Lead | pm.lead@ateraanalytics.com | 1.2, 5.3 | Aug | Feb
6.2 | Design for CAM 5G Data Processing | Lead & Application Developer | lead.appdev@ateraanalytics.com | 6.1 | Aug | Oct
6.3 | Prepare Data for AI Network Models | Lead & Application Developer | lead.appdev@ateraanalytics.com | 6.2 | Sep | Nov
6.4 | Design Machine Learning Path Planning | AI Specialist | ai.specialist@ateraanalytics.com | 5.6, 5.7 | Oct | Jan
6.5 | Train Models for Remote control Driving KPIs | PM/Lead & AI Specialist | pm.aispecialist@ateraanalytics.com | 6.1,5.6 | Nov | Feb
6.6 | Validate AI Models | Lead & AI Specialist | lead.aispecialist@ateraanalytics.com | 6.4,6.5 | Dec | Mar
6.7 | NVidia Digital Twin module deployment | Contractor | contractor@ateraanalytics.com | 1.2,1.3, 6.4 | Jan | Mar
6.8 | Automated Data acces via API | Application and Data Dev | app.datadev@ateraanalytics.com | 1.2,5.7,6.7 | Mar | Mar
7 | Final Delivery |  |  |  | Apr | Apr
7.1 | Full implementation of platform | Whole Team | team@ateraanalytics.com | 1,2,3,4,5,6 | Mar | Mar
7.2 | Project Reporting and Presentation | Whole Team | team@ateraanalytics.com | 7.1 | Apr | Apr