## Simple Gantt Chart - EX
Gantt Chart - Atera Analytics - Optimising Technology Feasibility for Autonomous and Remotely Controlled Vehicles
|  |  |  | 2025 | [8 empty] | 2026
[5 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
ID | Dependencies | TITLE | OWNER | EMAIL | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr
1.1 | 1.1 | TITLE: KOM - Zenzic and MSP; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
1.2 | NA | TITLE: Software Tools Selection and basic testing; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
1.3 | NA | TITLE: Hardware Tools Selection and basic testing; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
1.4 | 1.1 | TITLE: Meeting AI advisors on project setup; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
2 |  | TITLE: Route 10 Deliveres
2.1 | 1.1 | TITLE: Proof of concept algorithm and visual output for indicative large-scale automated assessment (eg regional).; OWNER: Collaborators - Route 10; EMAIL: collaborators@route10.com
2.2 | 2.1 | TITLE: Proof of concept algorithm with manual assistance and numerical/agentic output for indicative small-scale automated assessment (eg local); OWNER: Collaborators - Route 10; EMAIL: collaborators@route10.com
2.3 | 2.1 | TITLE: Report Including - Background Metholodogy and Conlcusions; OWNER: Collaborators - Route 10; EMAIL: collaborators@route10.com
2.4 | 2.2, 2.3 | TITLE: Provide code and documentations to Atera A.; OWNER: Collaborators - Route 10; EMAIL: collaborators@route10.com
3 |  | TITLE: Front End Application
3.1 | 1.2 | TITLE: Exploratory Data Analysis; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
3.2 | 1.2, 3.1 | TITLE: Develop visualisation and users intefaces; OWNER: Application Developer; EMAIL: app.developer@ateraanalytics.com
3.3 | 3.2 | TITLE: Rendering of POC Visualisations at interface; OWNER: Application Developer; EMAIL: app.developer@ateraanalytics.com
3.4 | 2.1,2.2,2.3 | TITLE: Visualisation of Route 10 Report; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
4 |  | TITLE: Project Management and Setup
4.1 | 1.1 | TITLE: Scope and Goal Setting; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
4.2 | 1.1 | TITLE: Quarterly Objectives Review & Planning; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
4.3 | 1.4 | TITLE: Session with advisors & stakeholders; OWNER: Whole Team; EMAIL: team@ateraanalytics.com
4.4 | 1.2 | TITLE: Web Tools Setup & Integration Environment; OWNER: Lead & Application Developer; EMAIL: lead.appdev@ateraanalytics.com
4.5 | 4.1 | TITLE: Training & Technical Events; OWNER: Whole Team; EMAIL: team@ateraanalytics.com
4.6 | 1.1 | TITLE: QRM 1 with Monitoring Officer; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
4.7 | 1.3 | TITLE: Hardware Setup; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
5 |  | TITLE: Data Integration and Architecture
5.1 | 1.2, 4.1 | TITLE: CAM Operations Data Enablement; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
5.2 | 1.2, 5.1 | TITLE: End to End Data Architecture Design; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
5.3 | 5.1 | TITLE: Validate EV CAM performance data; OWNER: Contractor; EMAIL: contractor@ateraanalytics.com
5.4 | 5.2 | TITLE: Digital Data Model Definition; OWNER: AI Specialist; EMAIL: ai.specialist@ateraanalytics.com
5.5 | 1.2,5.2,5.4 | TITLE: Data Integration with External Sources; OWNER: Application and Data Dev; EMAIL: app.datadev@ateraanalytics.com
5.6 | 5.2,5.5 | TITLE: AI Data Enrichment & Integration of Data Sets; OWNER: Lead & Application Developer; EMAIL: lead.appdev@ateraanalytics.com
5.7 | 5.4,5.6 | TITLE: Visualisation of Route Navigation Data; OWNER: AI Specialist; EMAIL: ai.specialist@ateraanalytics.com
6 |  | TITLE: CAM Integration and Testing
6.1 | 1.2, 5.3 | TITLE: Atera A. CAM Data API Connectivity; OWNER: PM/Lead; EMAIL: pm.lead@ateraanalytics.com
6.2 | 6.1 | TITLE: Design for CAM 5G Data Processing; OWNER: Lead & Application Developer; EMAIL: lead.appdev@ateraanalytics.com
6.3 | 6.2 | TITLE: Prepare Data for AI Network Models; OWNER: Lead & Application Developer; EMAIL: lead.appdev@ateraanalytics.com
6.4 | 5.6, 5.7 | TITLE: Design Machine Learning Path Planning; OWNER: AI Specialist; EMAIL: ai.specialist@ateraanalytics.com
6.5 | 6.1,5.6 | TITLE: Train Models for Remote control Driving KPIs; OWNER: PM/Lead & AI Specialist; EMAIL: pm.aispecialist@ateraanalytics.com
6.6 | 6.4,6.5 | TITLE: Validate AI Models; OWNER: Lead & AI Specialist; EMAIL: lead.aispecialist@ateraanalytics.com
6.7 | 1.2,1.3, 6.4 | TITLE: NVidia Digital Twin module deployment; OWNER: Contractor; EMAIL: contractor@ateraanalytics.com
6.8 | 1.2,5.7,6.7 | TITLE: Automated Data acces via API; OWNER: Application and Data Dev; EMAIL: app.datadev@ateraanalytics.com
7 |  | TITLE: Final Delivery
7.1 | 1,2,3,4,5,6 | TITLE: Full implementation of platform; OWNER: Whole Team; EMAIL: team@ateraanalytics.com
7.2 | 7.1 | TITLE: Project Reporting and Presentation; OWNER: Whole Team; EMAIL: team@ateraanalytics.com